## Progress
Sprint |  |  | ✓ | Tasks
From | To | Duration |  |  |  | Color Guide
2024-05-01 | 2024-05-26 | Bounding Period | TRUE | Getting engaged in the Community |  | Cancelled
|  |  | TRUE | Begin investigating RuxAiLab |  | Postoned
|  |  | TRUE | Porposal Presentaion to the Community |  | Reschuled in another sprint
2024-05-27 | 2024-06-13 | 2 Weeks | TRUE | Read More About Usability Test
|  |  | TRUE | Check Concept for Data Synthesis
|  |  | TRUE | Try System with Juca & Karine
|  |  | TRUE | Video Transcript
|  |  | TRUE | Study Sentiemnt for Video Transcript (Conversational Sentiment Analysis)
|  |  | FALSE | Check https://optuna.org/ for hyper Param Tunning
|  |  | TRUE | Check dialogue RNN
|  |  | TRUE | EDA for MELD
2024-06-14 | 2024-06-27 | 2 Weeks | TRUE | Check Timing for Assembly AI
|  |  | TRUE | Analyze Sentiment for sentences Per Speaker not whole utterance
|  |  | TRUE | Whisttle Sent By Karine
|  |  | TRUE | Whipsher Hugging Face Models
|  |  | TRUE | Study Flask
|  |  | TRUE | Build Complete Pipline
|  |  | TRUE | Check if Assmbly AI has its model on hugging Face
|  |  | TRUE | Try Pre-trained Models on hugging for repo erc(Context)
|  |  | TRUE | Check Deployment Services | Asked Murello
|  |  | TRUE | Check Wikki for Docs
|  |  | TRUE | Meet with Sebastiane for Integration
|  |  | TRUE | Check DialyDialgoue Dataset
|  |  | TRUE | Check Roberta Model
|  |  | FALSE | Check Marc's Paper Sent
|  |  | TRUE | Ask Karine: What do you think about idea about running more tests
2024-06-28 | 2024-07-11 | 2 Weeks (MidTerm at week 2) | TRUE | Begin Styudying Deployment | youtube/median
|  |  | TRUE | Build Docker Image for the Project | sentiment_analysis:v5
|  |  | FALSE | check async requests
|  |  | TRUE | Prepare documentataion wikki for Deployment Process
|  |  | FALSE | Try Docker Image on a cloud provider
|  |  | TRUE | Check with karine saving audio instead of video for faster inference
|  |  | FALSE | Use GPU inside Fast API
2024-07-12 | 2024-07-25 | 2 Weeks | TRUE | Study Vue
|  |  | TRUE | Study Vuetify Ninja Playlist
|  |  | TRUE | Check Karine Material For Vuetify
|  |  | TRUE | Clone Ruxailab Repo
|  |  | TRUE | UI Frames for sentiment Analysis Videos text
|  |  | TRUE | Present the UI to the mentors (Karine)
2024-07-26 | 2024-08-09 | 2 Weeks | TRUE | Setup Wave Surfer in RuxaiLab
|  |  | TRUE | Setup Axois in RuxaiLab
|  |  | TRUE | Integarted RuxailLab to API
|  |  | TRUE | Add End Point to take audio fie + time stamp
|  |  | TRUE | Check Firebase collection in RuxAiLab for sentimrnt result
2024-08-10 | 2024-08-23 | 2 Weeks (Final Evaluation) Buffer for Delays | TRUE | Audio Sentment Collection for Firebase
|  |  | TRUE | Controllers For AudioSentiment
|  |  | TRUE | Analysis Action For the Regions + Preview
|  |  | TRUE | Add Organsim for Transcriptions
|  |  | TRUE | Cooperators Part of the Test
|  |  | TRUE | Audio Wave Controller (Volumn + Speed)
|  |  | TRUE | Delete Segment Feature
|  |  | TRUE | Create PR to RunxAiLab
|  |  | TRUE | API Documenation
|  |  | FALSE | API Repo ReadMe
|  |  | TRUE | Complete Wikkis
|  |  | FALSE | Check Docker Image
|  |  | FALSE | Deployemnt
|  |  | TRUE | Fix Follow Up Sheet
|  |  | FALSE | Create Demo
|  |  | FALSE | Asyc APIs
|  |  | FALSE | Submit Final Evauation

## Meetings Log
Date | Time (UTC+3) | Attendees | Topic | Questions To Ask | Notes | New Tasks | Presentation Link
2024-05-14 | 16:30 - 17:00 | Marc | Welcome Meet | 1. We will focus on text/video answer [Marc: it depends on the System avalibality] 2. Pretrained/Scratch Model [Marc: No problem with Both It is Your Project] | ✔ Daily Meet ✔ Weely Community Meet Monday 19:00 (UTC+3) ✔ Work with SCURM ✔ Next Meet with presnetaion Thurdsay/Friday | ➜ Check DataSet avaliabilty with Karine ➜ Study other Opponents (Maze ....) ➜ Prepare Presentation for GSoC Proposal for the weekly meet with mentors | -
2024-05-20 | 20:00 - 21:00 | Weekly Meet By Community | Community Meet |  |  | ➜ Check Data ➜ Try System with JUCA | -
2024-06-04 | 17:00 - 18:00 | Karine Marc Juca Murello | Trying Tests and Data Issue |  | ✔ JUCA: Take Question in consideration for analyzing the answer ✔ Marc: Sentiment Analysis for text transcript ✔ Karine: Start Front End in paralle with Back End | ➜ Study Analysis for Audio Approach
2024-06-14 | 16:00 - 17:00 | Karine Murello | Ver.#1 Sentiment Analysis (Roberta) | 1. Real-time sentiment Processing or offline 2. More video with real users for systems they don’t know a lot (Ask Community For Help :D) 3. Current System Deployment (google cloud) - Deploy Model inside UI - Interface with API 4. Integration with Video by Sebastian | ✔ Karine: Focus Analysis for 1 Speaker only ✔ Murello: Check Microsoft Speech2Text API ✔ Murello: Separate the Q from A using like sound of asking like in GPT ✔ Karine: Analyize Inertval by Interval (Tester click next to analyize next interval) ✔ Murello: State of Art for sentiment analysis by Google Research ✔ Deployment check service by google cloudera ✔ Organize Meet with Sebastiane for Integration of Video & Text & Audio Sentiment ✔ Check Wikki & FAQs for Documentation for the Repo ✔ Next Meet We need to Find solution for the Speech2Text API ✔ Murello: We need to refine this version | ➜ Faster/Free Speech2Text API (Microsoft) ➜ Refine this initial Version ➜ Check Deployment Services ➜ Meet with Sebastiane for Integration ➜ Check Wikki for Docs | Presentation Meet#3 14-06-2024
2024-07-03 | 17:00 - 18:00 | Karine | Ver.#2 Sentiment Analysis + Docker Image | 1. One-sided Video Analysis 2. Saving audio file to the firebase for faster inference (I think ☺) 3. Do we need stream-lite 4. How will we integrate the api to RuxaiLab 5. Ideas about what to document for easier use by contributors 6. Any Docs Required for the Mid-Term Evaluation | ✔ Karine: Yes we already save the video of the session from each side so working on the evaltor's side will be perfect ✔ Karine: Take Care the BE (API) needs to be independent from RuxAiLab ✔ Karine: Perfect I see you have learned alot of new technologies (Docker - Flask ....) ✔ Karine: Next Phase will be integrating API to RuxAiLab ✔ Karine: Regarding the Deployment of the BE we just need to prepare the Docker File and it will be easy to deploy on google cloud | ➜ Study Vuetify ➜ Study Vue ➜ Begin in UI Design Screens | Presentation Meet#4 03-07-2024
2024-08-02 | 21:00 - 22:00 | Karine | UI Brain Storming | 1. How can we preview this transcript 2. The audio file may cause http request timeout | ✔ Karine: We can Make just analyize timestamp not the whole audio ✔ Karine: We will have mutilple aswers per the same test so we need a left drawer for showing sentiment of different answers :D | ➜ Fix the UI ➜ Begin UI Imeplentation ➜ Create new end point to analyize only segement of the audio file not the whole audio file | Figma UI Screens
2024-08-12 | 20:00 - 21:00 | Karine | Integration to RuxAiLab | 1. I think we need to have another meet next week for follow up (Sat) 2. Do you see Another Tasks 3. Regarding the final submission what is expected to be prepared 4. Do we need to show other mentors our progress before submission 5. We need to stop coding at Sunday and make sure to finish documentation then we can continue coding 6. Can we submit the project without API Deployment ( To be checked later → But we have an already running Image) 7. PRs 8. What about other contributors asking on Discord | ✔ Karine: We have tasks no need to add more ✔ Karine: Prepare perfect read Me for the API ✔ Karine: No need for BLog just the readme and wikkis links ✔ Karine: I think we will have a meeting with the mentors but to e confirmed ✔ Karine: FIx the Bug in the FireBase Collection for the audio Sentiment ✔ Karine: Don't allow contribuotrs to push in the code until GoSC ends | ➜ Fix Model Structrue ➜ Transcription Section ➜ Delete Region ➜ Cooperators Section ➜ Add Time to Timeline ➜ Follow Up Meet Next Monday ➜ Refactor BE (Small Part) ➜ API Documentation ➜ BE ReadMe ➜ Check Docker Image | Presentation Meet#5 12-08-2024
2024-08-19 | 22:00 - 23:00 | Karine | Finalizing Integration to RuxaiLab | 1. Show up the completed features till now 2. Check the Required Docuemntation for the Final Submission 3. When will we show other mentors the progress 4. Check Pull Request | ✔ Karine: Perfect till now ✔ Karine: Just Finsih the Docuemntaion then later we can add more features ✔ Karine: All We need to submit for the Final Evaluation is the API Repo Link with the ReadMe ✔ Karine: Add Follow Up Sheet Link , Wiikki Links, PR Request in teh API ReadMe ✔ Karine: We can have a presentaion to show off our work to Mentors ✔ Karine: We need to check with Dr.Marc his ideas for writting the research paper | ➜ Complete Follow Up Sheet ➜ API Repo ReadMe ➜ BE Documentaion ➜ Fix Env Issue for the Flask ➜ Fix Docker Image ➜ Submit the Final Evaluation to GSoC [deadline: 29th Aug] | Presentation Meet#6 19-08-2024

## 2-Day Logs
Date | Task Done | Notes
2024-06-09 | 1. Study More about Conversational Sentiment Analysis
2024-06-12 | 1. EDA for MELD 2. Try to use ERC (Failed)
2024-06-13 | 1. Produed Transcript for the last min for JuCA's and Video (Version 1) 2. Weekly Meet with Karine | • Assembly AI API is very slow and can't get transcript for the whole video • Non related utterances at the beginning of the vide [Karine told me they are neutral, I need to try it with the sentiment model].
2024-06-16 | 1.Fixed Issue for Assembly AI Latency 2. Entered Meet with Sebastiane For Discussing Integration between Video & Text Analysis | • 100hr free trial , 0.12$/hr pay as you go • I need to update the UI but next week (Approved by Karine)
2024-06-17
2024-06-23 | 1. Study Flask 2. Build Complete Pipline (Locally CPU) [Local File, drive file) | • Check usage of firebase storage with assembly ai • Karine prefers using open Source librray for transcript
2024-06-25 | 1. Tried Whispher Hugging Face Models (Tiny-base-small) 2. Created Small Reccord as Demo By Basma about Sportify (1 Sided) 3. Created Endpoints for whispher model Sizes and Saved Examples 4. Tried to integrate using GPU for inference(But Failed)(To Be fixed Later) | • I need to start Studying Deployment to check model sizes we are uising • Tiny Whisper Model results are bad, abse & small are better • To Fix the issue of using GPU for Inference • Assembly AI transcripted the whole video by Basma into 3 utternaces only becuase i am the same speaker :D • Check if the model for assembly AI is on hugging face and use our local resource isntead of the API
2024-06-28 | 1. Study Deployment Process Steps 2. Check cloud providers services 3. Seach about google cloud services (gpu) | • We don't need GPU , just cpu • I need to prepare the docker image for the app
2024-06-30 | 1. Study Docker 2. Fixed Bugs with the images | • I need to run docker on linuax :D due to configuaration issued with windows • I was able to get sentiment for the 2 videos in 50s, 3 mins respectively using the image v5 • conatiner run: docker run --name ruxailab -p 8000:8000 -v /media/basma/basmavolume/sentiment-analysis-api/demos:/sentiment_analysis_app/demos sentiment_analysis:v5 • I need to study the async request • Need to use the video source from firebase not locally • I think better time to have the audio saved instead of video (better time) [check that with Karine]
2024-07-03 | 1. Weekly Meet with Karine
July 5 - 16, 2024 | Buffer Period Due to University Project Submission [Approved by the Mentors]
2024-07-18 | 1. Study Vue Crash Course (playlist) | Ninja Tutorial
2024-07-23 | 1. Study Vuetify Crash Course ( Tille lession 22) 2. Clone Ruxailab | Karine Sent Me Vuetify Material
2024-07-25 | 1. Search for audio UI Libraries 2. Fix the denepnecises for wavesurfer
2024-07-25 | 1. Begin in UI Design
2024-08-02 | 1. UI Brain Storming Meet with Karine
2024-08-06 | 1. Created API splitting audio by silence 2. Created api to process sentiment on chunks 3. Created API for senitment Analyisis by timestamp | The first and second apis are still in code but karien told me to focus on the third one so that we need to make this project independent from ruxailb
2024-08-08 | 1. Fix WaveSurfer Setup Errors 2. Setup Axois in Ruxailab 3. Inetgrated API (Hello World) to Ruxailab
2024-08-10 | 1. Integrated Wave Surfer to Read from Firebase 2. Setup Axois for FireStore to be able to Download the Files from to Project 3. Fixed Flow for Wave Surfuer Initilization 4. Created Collection for Audio Sentiment in FireBase 5. Created UI for showing processed Regions (Per Color) 6. Created Wikki For Vue and Vuetify Study Guide
2024-08-12 | 1. Follow Up Meet with Karine
2024-08-14 | 1. Fix Model for Sentiment Analysis to have a unique id by firebase 2. Added QueryFucntion in teh Base controller to be abe to craete query with mulptie conditons 3. Created Transcription Section 4. Created Play Segemnt Function to be able to play specific segemnt in the Audio 5. Added Timeline to the Audio Wave 6. Added Dcoumeation for the Audio Sentiment Model file and Audio Sentiment Controller
2024-08-16 | 1. Created Delete Segemnt Function 2. Added Speed Audio Wave Controller 3. Added Volume Audio Wave Controller 4. Merged develop Branch to audio-sentiment-analysis and fixed conflicts 5. Created the PR for RuxAiLab
2024-08-19 | 1. Created the template for the API Repo READMe 2. Follow Up Meet With Karine for Final
2024-08-20 | 1. Completed the Follow Up Excel Sheet 2. Fixed Virtual Environment Bug For Flask App 3. Added Swaager API Docs Generator to the APP 4. Refacotored postman Collection to be shared
2024-08-21 | 1. Speech2Text-Tools-Survey Wikki Done 2. BE Repo README

## Initial Project Timeline
Tasks
Start | End | Duration | Label
2024-05-01 | 2024-05-15 | 15 | Engage in Community
2024-05-16 | 2024-05-26 | 11 | Discuss Tools with mentors
2024-05-16 | 2024-05-26 | 11 | Fix Timeline
2024-05-27 | 2024-05-31 | 5 | Read more on usability tests
2024-05-27 | 2024-05-31 | 5 | Competitors Study
2024-06-01 | 2024-06-06 | 6 | Proof Concpet
2024-06-07 | 2024-06-14 | 8 | Data Analysis / Preprocessing
2024-06-15 | 2024-06-18 | 4 | Data Loaders
2024-06-19 | 2024-06-23 | 5 | Build Arch
2024-06-24 | 2024-06-28 | 5 | Tarin/ Eval Model
2024-06-29 | 2024-07-03 | 5 | Build Back End
2024-07-04 | 2024-07-08 | 5 | Deployment
2024-07-09 | 2024-07-12 | 4 | StreamLine
2024-07-13 | 2024-07-19 | 7 | Front End Screen
2024-07-20 | 2024-07-23 | 4 | Integration to RUXIALAB
2024-07-24 | 2024-07-26 | 3 | Fixing integration errors
2024-07-27 | 2024-08-02 | 7 | Testing
2024-08-03 | 2024-08-06 | 4 | Code Refctoring
2024-08-07 | 2024-08-10 | 4 | Documentation
2024-08-11 | 2024-08-24 | 14 | Buffer For Delays
2024-08-25 | 2024-08-24 | 0
2024-08-25 | 2024-08-24 | 0
Insert new rows above this one
Milestones
Date |  |  | Label
2024-05-01 |  |  | Start, May 1
2024-05-27 |  |  | Sprint #1
2024-06-15 |  |  | Sprint #2
2024-06-29 |  |  | Sprint #3
2024-07-13 |  |  | Sprint #4
2024-07-27 |  |  | Sprint #5
2024-08-11 |  |  | Sprint #6
2024-08-25 |  |  | Deliver, Aug 25
Insert new rows above this one